## Completed
Story Id | Title | Labels | Iteration | Iteration Start | Iteration End | Type | Estimate | Current State | Created at | Accepted at | Deadline | Requested By | Description | URL | Owned By | Owned By
97842560 | Create Test Plan (Austin) |  | 1 | 2015-07-06 | 2015-07-12 | feature | 2 | finished | 2015-06-25 |  |  | Girish Ranade |  | https://www.pivotaltracker.com/story/show/97842560
97842496 | Develop Help Text (Austin) |  | 1 | 2015-07-06 | 2015-07-12 | feature | 1 | finished | 2015-06-25 |  |  | Girish Ranade | Create text for 'Need Help' button Help Page | https://www.pivotaltracker.com/story/show/97842496 | Girish Ranade | Austin Fadely
98182844 | Validate FDA API |  | 1 | 2015-07-06 | 2015-07-12 | feature | 1 | finished | 2015-07-01 |  |  | Girish Ranade | Validate connection to the API and ensure that result sets are consistent with the search criteria provided. | https://www.pivotaltracker.com/story/show/98182844 | Girish Ranade
97632002 | Search for Recalls in my State |  | 1 | 2015-07-06 | 2015-07-12 | feature | 2 | finished | 2015-06-23 |  |  | Girish Ranade | If I provide my state, I would like to be able to search for food recall events in my state and filter the results to food recall events where the status = "Ongoing" and order by Classification = "Class I" then "Class II", then "Class III". I would like to see results in a way that I can quickly determine if this is a product I might shop for by seeing the Product Description and other relevant information in a list view. Other information like Recalling_Firm, reason_for_recall, report_date may be provided to the degree it can be easily displayed in a list format. For State look into 'Distribution Pattern' field and not 'State' field which is the state for the actual company and not necessarily the state of the recall | https://www.pivotaltracker.com/story/show/97632002 | Girish Ranade
97633356 | Allow user to scroll through all relevant data |  | 1 | 2015-07-06 | 2015-07-12 | feature | 2 | finished | 2015-06-23 |  |  | Girish Ranade | If the text behind certain fields and topic areas are lengthy (beyond the real estate of the screen), I would like to make sure that the application can allow me to scroll down to view all relevant information and scroll back (or back up to the next topic level above the current one) - or provide some form of "Read More". | https://www.pivotaltracker.com/story/show/97633356 | Girish Ranade
97633038 | Allow further search beyond State selections |  | 1 | 2015-07-06 | 2015-07-12 | feature | 2 | finished | 2015-06-23 |  |  | Girish Ranade | If a recall distribution pattern includes the US (or nationwide or similar expression), then include that in the list of recall events to show to user. | https://www.pivotaltracker.com/story/show/97633038 | Girish Ranade
98037616 | Color pallette for website |  | 1 | 2015-07-06 | 2015-07-12 | feature | 1 | finished | 2015-06-29 |  |  | Girish Ranade | Return to Search feature from any screen | https://www.pivotaltracker.com/story/show/98037616 | Girish Ranade
97631792 | Display Recall Events in my State |  | 1 | 2015-07-06 | 2015-07-12 | feature | 2 | finished | 2015-06-23 |  |  | Girish Ranade | I (food shopper in the US) would like to search for food recall events in my area (state), so that I can be knowledgeable about hazardous food recalls and avoid those foods if necessary. For State look into 'Distribution Pattern' field and not 'State' field which is the state for the actual company and not necessarily the state of the recall | https://www.pivotaltracker.com/story/show/97631792 | Girish Ranade
97632950 | See Relevant Details on each recalled item |  | 1 | 2015-07-06 | 2015-07-12 | feature | 1 | finished | 2015-06-23 |  |  | Girish Ranade | If I select a specific recall event, I would like to see any relevant details about that event that might aid me in identifying and avoiding any recalled food I may wish to shop for. This would include fields like: recall_number, reason_for_recall, status, distribution_pattern, product_quantity, recall_initiation_date, event_id, product_type, product_description, city, recalling_firm, report_date, voluntary_mandated, classification, code_info. | https://www.pivotaltracker.com/story/show/97632950 | Girish Ranade
97633190 | Allow pagination information to be displayed |  | 1 | 2015-07-06 | 2015-07-12 | feature | 1 | finished | 2015-06-23 |  |  | Girish Ranade | As a user I would like to see on each page how many records are remaining in my search list. Success Criteria : Some indication of how many total pages of search lists are available and on which page the user is, will be required | https://www.pivotaltracker.com/story/show/97633190 | Girish Ranade
97633264 | Return to Search feature from any screen |  | 1 | 2015-07-06 | 2015-07-12 | feature | 1 | finished | 2015-06-23 |  |  | Girish Ranade | At all times during use of the application, I would like to be able to return to the search feature (to start a brand new search), or return to the application home page at any time with a single touch or click. | https://www.pivotaltracker.com/story/show/97633264 | Girish Ranade
97842530 | Create Solution Design Document (Jamil) |  | 1 | 2015-07-06 | 2015-07-12 | feature | 1 | finished | 2015-06-25 |  |  | Girish Ranade |  | https://www.pivotaltracker.com/story/show/97842530 | Girish Ranade
97844476 | Develop Text for 'Fuzzy Search' field |  | 1 | 2015-07-06 | 2015-07-12 | feature | 1 | finished | 2015-06-25 |  |  | Girish Ranade |  | https://www.pivotaltracker.com/story/show/97844476 | Girish Ranade
98143594 | No Javascript |  | 1 | 2015-07-06 | 2015-07-12 | feature | 1 | finished | 2015-06-30 |  |  | Austin Fadely | As a(n)â€¦ Food shopper in the US Usingâ€¦ a non JS enabled browser I would Like toâ€¦ know why my browser won't display the form So thatâ€¦ I can either leave or find a browser that uses Javascript | https://www.pivotaltracker.com/story/show/98143594 | Girish Ranade

## Backlog Items
Id | Title | Labels | Iteration | Iteration Start | Iteration End | Type | Estimate | Current State | Created at | Accepted at | Deadline | Requested By | Description | URL | Owned By | Owned By
98036472 | View Help Text |  | 2 | 2015-07-13 | 2015-07-19 | feature | 1 | unstarted | 2015-06-29 |  |  | Girish Ranade | As a(n)â€¦ Food shopper in the US Usingâ€¦ my IOS or Android / mobile device I would Like toâ€¦ view help text on the form, So thatâ€¦ I know what the form is for and how to use it. Acceptance Criteria "-Help text for the form itself displays on the page. -Help text for each individual search field displays as well." | https://www.pivotaltracker.com/story/show/98036472 | Girish Ranade
98036828 | Regardless of Classification |  | 2 | 2015-07-13 | 2015-07-19 | feature |  | unstarted | 2015-06-29 |  |  | Girish Ranade | As a(n)â€¦ Food shopper in the US Usingâ€¦ my IOS or Android / mobile device I would Like toâ€¦ search all recalls in my State without having to narrow it down to a single classification (Class I, II, or III), So thatâ€¦ I can have a list of all recalls in my state on hand. Acceptance Criteria -Select state and click search. All results with a distribution pattern covering the selected state should show in the results. Can confirm by viewing multiple classes in the results list. | https://www.pivotaltracker.com/story/show/98036828
98201150 | Direct users to an 'Error Message' on Error |  | 2 | 2015-07-13 | 2015-07-19 | feature |  | unstarted | 2015-07-01 |  |  | Girish Ranade | Suggested error conditions Server is Down Invalid or Bad request to the API | https://www.pivotaltracker.com/story/show/98201150

## For Future Releases
Id | Title | Labels | Iteration | Iteration Start | Iteration End | Type | Estimate | Current State | Created at | Accepted at | Deadline | Requested By | Description | URL | Owned By | Owned By
98460892 | Add a button to display 'About this page |  |  |  |  | feature |  | unscheduled | 2015-07-06 |  |  | Girish Ranade | As a user I would like to have the ability to select an option on the screen to display information about the page and to explain the functionality of each page | https://www.pivotaltracker.com/story/show/98460892
98451714 | Broaden logic for State search |  |  |  |  | feature |  | unscheduled | 2015-07-06 |  |  | Girish Ranade | The state field is not stored consistently in the distribution_pattern field. for example Michigan can be entered as MI or Michigan, it can also be included in Nationwide, National, ALL US. The query string will need to be enhanced to allow for these. | https://www.pivotaltracker.com/story/show/98451714
98293082 | No Console Errors detected |  |  |  |  | feature |  | unscheduled | 2015-07-02 |  |  | Austin Fadely | As a(n)â€¦ FDA Stakeholder Usingâ€¦ I would Like toâ€¦ know that the code is elegant and has no errors So thatâ€¦ I know the form is optimized to its greatest potential. | https://www.pivotaltracker.com/story/show/98293082
98036662 | MInimize the number of clicks |  |  |  |  | feature |  | unscheduled | 2015-06-29 |  |  | Girish Ranade | As a(n)â€¦ Food shopper in the US Usingâ€¦ my IOS or Android / mobile device I would Like toâ€¦ view the most relevant information on recalls and conduct additional searches with as few clicks as possible, So thatâ€¦ I can get the information I want as quickly as possible and with as little hassle as possible. Acceptance Criteria "-1-click drilldown for product detail page. -1-click to go back to search panel." | https://www.pivotaltracker.com/story/show/98036662
98036400 | Report food problems |  |  |  |  | feature |  | unscheduled | 2015-06-29 |  |  | Girish Ranade | As a(n)â€¦ Food shopper in the US Usingâ€¦ my IOS or Android / mobile device I would Like toâ€¦ report issues I've encountered with foodstuffs to the FDA, So thatâ€¦ I can help the FDA place recalls as quickly and with as much information as possible. Acceptance Criteria "-User can fill out a form that sends an email to the FDA. -Form has fields for the user's name and email, as well as the UPC code of the product. -Form has help text (with images if possible) to show user where to find the UPC code on the product. -Form has field to describe the backstory and what symptoms/affects they are experiencing. -Form has on-screen confirmation that sending was successful." | https://www.pivotaltracker.com/story/show/98036400
98143552 | Simple and elegant display |  |  |  |  | feature |  | unscheduled | 2015-06-30 |  |  | Austin Fadely | As a(n)â€¦ Food shopper in the US Usingâ€¦ my IOS or Android / mobile device I would Like toâ€¦ see only buttons that are relevant and meaningful to me So thatâ€¦ I do not waste time clicking buttons that are not useful. | https://www.pivotaltracker.com/story/show/98143552
97631898 | Provide Functionality on a variety of browsers |  |  |  |  | feature |  | unscheduled | 2015-06-23 |  |  | Girish Ranade | I would like to use a variety of typical mobile and web-browser-based devices in order to view this information so that I can obtain information from any location where I have internet and/or WiFi service. | https://www.pivotaltracker.com/story/show/97631898
98036556 | Sort by options - default |  |  |  |  | feature |  | unscheduled | 2015-06-29 |  |  | Girish Ranade | As a(n)â€¦ Food shopper in the US Usingâ€¦ my IOS or Android / mobile device I would Like toâ€¦ sort results by different criteria, i.e.: date and class, So thatâ€¦ I can view the results in a way that makes sense to me. Acceptance Criteria "-Options exist to sort the results by date or recall company. -Changing the sort re-lists the results in a way that matches the expected behavior for sorting." | https://www.pivotaltracker.com/story/show/98036556
98036748 | Number of results per page dropdown (default set to 10) |  |  |  |  | feature |  | unscheduled | 2015-06-29 |  |  | Girish Ranade | As a(n)â€¦ Food shopper in the US Usingâ€¦ my IOS or Android / mobile device I would Like toâ€¦ change the number of results on the list page, So thatâ€¦ I can view more or less results. Acceptance Criteria "-Dropdown for different list sizes (10, 20, 50) -Changing the dropdown increases or decreases the number of items displayed on the page so that the number of results matches the value in the dropdown." | https://www.pivotaltracker.com/story/show/98036748
98182464 | Allow users to provide Feedback |  |  |  |  | feature |  | unscheduled | 2015-07-01 |  |  | Girish Ranade | Provide a link to a Feedback Form allowing users to provide comments or suggestions. | https://www.pivotaltracker.com/story/show/98182464
98036316 | Scan my shopping carts for Recalls |  |  |  |  | feature |  | unscheduled | 2015-06-29 |  |  | Girish Ranade | As a(n)â€¦ Food shopper in the US Usingâ€¦ my IOS or Android / mobile device I would Like toâ€¦ compare items in my online shopping cart (various retail websites) to FDA recalls on that same items, So thatâ€¦ I can make sure that what I'm buying is under recall from the FDA. Acceptance Criteria "-User can activate a browser extension which scans the UPC codes of all items on the current page (assuming it is a shopping cart). -When scan is complete, the report will show UPC codes of products in the cart with recalls on them as well as a link to view the specific information on the recall. If possible, the report would show the class as well without the user having to click again." | https://www.pivotaltracker.com/story/show/98036316
98036088 | Subscribe to Food Recall Alerts |  |  |  |  | feature |  | unscheduled | 2015-06-29 |  |  | Girish Ranade | As a(n)â€¦ Food shopper in the US Usingâ€¦ my IOS or Android / mobile device I would Like toâ€¦ subscribe to receive notifications on recalls that may affect my area, So thatâ€¦ I can always be aware of potential issues with foods I buy. Acceptance Criteria: "-User can subscribe to a list using a valid email address and select which states they'd like to receive alerts for. -User receives an email address anytime a new recall happens where the distribution covers the selected state, including nationwide recalls. -Email contains the same information as the recall detail page." | https://www.pivotaltracker.com/story/show/98036088
97945562 | Research End to End Testing tools |  |  |  |  | feature |  | unscheduled | 2015-06-27 |  |  | Girish Ranade | Research tools - i.e Protractor - to conduct e2e testing. Protractor designed for Angular js. https://angular.github.io/protractor/#/ | https://www.pivotaltracker.com/story/show/97945562
98461088 | Add ability to share recall details with a Facebook connection |  |  |  |  | feature |  | unscheduled | 2015-07-06 |  |  | Girish Ranade | As a user I would like to share recall detail information with my Facebook friends so that I can help them stay informed about recalls in their state. | https://www.pivotaltracker.com/story/show/98461088
98037236 | Section 508 compliance |  |  |  |  | feature |  | unscheduled | 2015-06-29 |  |  | Girish Ranade | As a(n)â€¦ Food shopper in the US with limited vision Usingâ€¦ my computer for the visually impaired I would Like toâ€¦ use this form with my specialized web-browsing software So thatâ€¦ I can view and use the search form Acceptance Criteria -Pages pass the WAVE test with 0 critical errors. http://wave.webaim.org/ | https://www.pivotaltracker.com/story/show/98037236
98524280 | Testing with unrealistic data does not generate a "No data selected" message |  |  |  |  | feature |  | unscheduled | 2015-06-29 |  |  | Girish Ranade | As a user I want to be notified each time I enter search criteria that does not yield a result set Acceptance Criteria The first search with bad data i.e &^@%^& yields no results but does not display an error. All subsequent searches with bad data do yield an error message | https://www.pivotaltracker.com/story/show/98524280